## Dashboard
Green – On Track , Yellow – Attention Required, Red – Immediate Attention Required | N
Project | Scope | Cost | Schedule | Risk | Issue | Next Steps / Comments | Overall Project Health | Code | Status
Single Window Initiative | 2 | 2 | 2 | R1. Low trade uptake poses challenges for benefits realization |  | • Transfer of OPI responsibilities by Q4. • EC-FIPT for close out on March 28 | Green | 2 | On Track
Establishment Licensing and Inspections | 2 | 2 | 2 | R1. Lean Analysis/Business Transformation contract may lead to delays in requirements completion R2. Contracting vehicles R3. IDMP integration with 628 R4. Enterprise IM architecture can easily expand/deviate scope for current stage deliverables | I1. OCS is likely to be de-scoped as their program is looking to NDS (National Drug Control System) to fulfill need I2. Other programs need to be considered in the design of the solution (GCP, AHRA/Semen, Cannabis, etc). Change request are being put forward for 2 programs. | • EARB review scheduled with TBS May 2019 • IM architect working with WG and BREAD, deliverables with timelines need to be set • Continue business requirement elicitation • PIA work to be packaged and finalized - no PIA required for IP628 ($40K in current FY, $80K next FY) • Initiate Change request : 1) Add GCP/AHRA 2) Potential removal of OCS • TA for Change Management Contract, other resources needed in FY 19/20 • Engage PSPC for upcoming RFP • Governance committee meeting lined up for April (Project monitoring committee, DG-SC, ADM committee) | Yellow | 3 | Attention Required
Drug Shortages | 2 | 2 | 2 | R1. New/revised enhancements identified R. Change in project ownership |  | • R2.4 under development with vendor - production release date Mar 31. • Development will be done in 3 phases with HC performing UAT for 2 days after each phase. • Phase 1 & 2 of UAT complete, Phase 3 in dev with vendor. • Progarm to finalize demo script, send invitations • Decision has been made to exercise the two option years - work with vendor to formalize. • Work with program and GS1 Canada to incorporate GTIN in to shortage and discontinuation reports | Green | 2 | On Track
ROEB Data Analytics & Business Solutions | 2 | 2 | 2 |  |  | • BEC-CET approved for CoP governance • CoP Meeting with new Chair to discuss ToR, DASR, BEC CET (March 27) • Supporting HPCD with directorate D+A strategy • Data quality workshop and training (April 2) • Introductory SAS Training (Q1) • Assisiting IMSD SAS Grid Production testing (Mar 31) • Data Quality Framework (Q3 2019-2020) • Data Management & Governance Framework (Q4 2019-2020) • DASR revision (March 14) • EC03/EC04 available in April. | Yellow | 2 | Attention Required
ROEB Electronic Licensing and Global Supply Chain Mapping | 2 | 2 | 2 | R1. Undefined business problem makes identifying appropriate solutions difficult | None | • Requirements gathering workshops planned for early March | Green | 2 | On Track
Enabling Compliance and Enforcement Program Delivery | 2 | 2 | 2 | R1. Business commitment: Ensuring that businesses can allocate resources to the development of a Jira or Edubrite instance. R2. Hosting : IMSD approval is required to host a prod environment. R3. Prone to scope expansion | None | Next LMS steps: • Health Product Inspection and Licensing: continuing to populate with courses/programs as they are provided from the program. Aiming for completion and pilot roll-out by FY end • Tobacco & Vaping: re-initiated regular meetings, continuing to develop programs and courses. • Pesticide Compliance: Expressed interest in an LMS instance. Meeting Week of Mar 3 to discuss and agree on a rollout plan Next Jira steps: • Migrate Jira from development to its production server. • New instance for Controlled Substances (March 2019) • New instance for Laboratories (May 2019) | Green | 3 | On Track
ROEB Aging IT (Stabilization/Modernization/Transformation) | 2 | 2 | 2 | R1. Competing priorities within IMSD, SSC and business groups could delay work R2. Volume of work may increase and cause workload issues |  | • Continue work with IMSD and Alain Barriere to migrate & decomm apps on W2K8. Alain has completed transfer of apps to new servers. • Leverage Final report for IT strategy and addressing high risk applications. Initially focussing on highest risk applications (Statuts IM, Tobacco Control Program Activities). • Statuts IM: Alain Barriere was able to move Statuts IM to DELIM db already upgraded as part of W2K8 project. Currently testing to verify. •TCPA: Business owner confirmed they will no need app after around April 2019. Will set app to decommission. | Green | 2 | On Track
Drug and Health Product Inspections Database | 2 | 2 | 1 | R1. Resource intensive for both IMSD and SME | I1. Changes to DHPID will be required for next FY due to implementation of AHRA, as well as new MD action plan. The scope of these changes is unknown, as such the impacts and cost are unknown. I2. Delays have pushed deployment beyond March 31st. | • TRA in final stages, draft complete and will begin sign off for completion by Feb 28th • Software installation complete, IMSD undgoing QA testing. Working to resolve issues with connectivity in new tenancy. • UAT Cycle 1 Enhancement work completed, 3 JIRA issues remain with IMSD for fix. • Work started on remaining 4 programs in API, revisions to first 3 programs. | Yellow | 1 | Attention Required
Modernizing the ROEB Employee eToolkit | 2 | 2 | 2 | R1. Industry may be resistant to uploading their data into the cloud (epost Connect) R2. Staff may be hesitant to use new technology, if they’re not familiar with it. | I1. IT warehouse temporarily depleted stock of smartphones; This is causing a delay in delivery of devices to some users. New bulk shipment of iPhones expected by March 31st. I2. Testing of virtual workstation delayed due to competing priorities with cloud team. They're expecting a new member soon and hope to be able to provide timeline soon. I3. Smartpen pilot delayed while working to get approval from IT Security. | • Priority order placed for tablets (40)/smartphones (218) to try to fill all remaining needs this fiscal. • 2nd tablet order (105) now starting to be deployed to end users. (CSPEHD, CPSTPD, Labs) • 1st tablet order (80) delivered to end users (CPSTPD). • Virtual Workstation: To be tested by inspectors (HPC, TVC) prior to planned deployement next fiscal. • Epost Connect: Contract renewed Feb 25th. IAO extended to end of 2019 while Canada Post completes necessary security assessment. | Green | 1 | On Track
Border Compliance IT Modernization | 2 | 2 | 1 | R1. Partners want scope change R2. Novel software implementation for GoC. |  | • Gate 2 EC-FIPT approval obtained on Nov 29th. • Stage 3 Kick-Off on Nov 13th. • Detailed BRD and PMP feedback received. • PIA work initated. • Gate 3 delayed till March to allign with IP603 costing requirements.
Quality Management System | 2 | 2 | 2 | R1. Complex Space with vocal stakeholders and various branches implicated may cause scope creep. R2. Limited IMSD/SSC capacity may negatively impact project timelines (OA completion timelines etc). As a result, timelines may shift slightly for Gate 2 completion. R3. Timelines are at risk due to late start of the HLBRD Review and OA initiation. All lead time has been diminised and now timelines are at risk of Gate 2 delay. | I1. Bugs and Issues are causing certain programs to worry about upcoming audits (MRA implications) | • HLBRD and Project Charter Final Drafts sent to IMSD and OA Team for review and initiation of OA process. • OA initiation on January 16 2019 (following peer review). • OA lead to provide evaluation criteria and list of potential vendors by February 1 2019 (demos to be set shortly after). • First draft of OA to be completed by end of February 2019. • Continue to work on other Gate 2 artifacts ( Business Case, PCRA, Costing Model, Project Plan etc) to both help supplement OA and to line up program and gov. approval.
ROEB IM Strategy Plan | 2 | 2 | 1 | R1. GCdocs roll-out schedule for regulatory branches has been changed from FY 19/20 to FY 18/19 pending approval on May 10th. R2. Delays in receiving information and/or decisions from Corporate partners. | I1. Staffing and Training in March has slowed down our ability to implement our work plans and execute the IM strategy as initially laid out. | • Confirm priorities for FY 2018/19 • Operational readiness for the deployment of GCdocs • Revise and Execute Awareness & Training Work Plan
GCdocs Project | 2 | 2 | 1 | 1. Inability to configure a common folder structure across all the regulatory branches that takes into account all the common regulatory business processes. 2. Limited IMSD capacity and inadequate planning negatively impacting RORB project timelines and deliverables. 3. Poor engagement from program areas and/or the absence of proper representation (identified SMEs) in the information architecture working group sessions. 4. Multi-branch and multi-program complexity complicates the ability for an enterprise solution that meets all indivual program needs. | 1.Various systems and databases currently being used to store information will need to be granted exemptions. 2. Feasibility of using GCdocs to view and store media files (i.e. videos) in the long-term. | • Work with SMEs to identify exceptions and devise a plan/strategy to deal with them • Continue to work with IMSD and the other Regulatory Branches to configure common folder structure • Continue to post artifacts on GCConnex and complete IM video • Execute next phase of communication approach • Continue to evaluate and monitor progress to date, schedule third WG sessions and discuss immediate impacts on the implementation date • Develop a document that will describe the management of issues and the support model for GCdocs during and post implementation
DAS Modernization | 2 | 2 | 2 | R1. Security assessment may limit the technology options available for the project. R2. Procurement of suitable COTS R3. Containment of costs R4. Scope expansion to include all current LIMS programs as part of an enterprise approach | N/A | • Engage DAS partners (law enforcement, provincial governments) • First draft of HLBRD has been shared with IMSD • Documentation of the project charter is 90% complete | Green | 2 | On Track
Project Cyclops | 2 | 2 | 2 | R1. Inability to find the right technical resources. R2. Tecnology required not ready for deployment. R3. Existing HC infrastructure not compatible with solution. |  | • Project kick-off meeting on Nov 13 with programs. • Program and data requirements defined. • Professional services secured, and contract initiated on January 23, 2019. | Green |  | On Track
Gadget Phase I |  |  |  | R1. Continuous Deployment method has been preferred over traditional approach to reduce risk to our business holders but it increases difficulty for developers. R2. So far Blockchain implementation in government has been very limited. Although it opens up a new avenue to build better trust and transparency with government's stakeholders, such new technology might show scalability problems early on. R3.. Drastic changes in how internal stakeholders receive and consume inspection data. R4. No dedicated project designer was hired (or planned). | I1. Actual inspection process turned out to be somewhat more complex and resource intensive than expected during planning phase. I2. Team members either being sick or having issues collaborating due to personal/professional commitments. I3. No front-end developer was initially hired. I4. Implementing decentralized file server with Gadget back-end. | • Work with a graphics designer to enrich user interface of the current product. • Complete Minimum viable product (MVP) with Blockchain implementation before March 31, 2019. • Work with graphics designer to implement design templates. • Approve and acquire funding for Gadget Phase II • Acquire the cut images from CSS cutter and apply to Gadget template. | Green |  | On Track
Hummingbird |  |  |  | R1. Although at first glance drones look like the biggest challenge, it's the image processing and resources needed to accommodate such a system which will pose the greatest risk. R2. Transport Canada's UAV regulations. | I1. Using drones in indoor setting has risen as a potential issue. | • Access feasibility of virtual inspection by discussing with related domain experts. • Explore areas of opportunity through focus groups and engagement sessions with Cannabis domain experts • Establish a task team to define use cases. • Submit Solutions fund, Stream I proposal by October 19th, 2018. • Key Business Requirements and Features for MVP was completed January 25, 2019. • Develop Feasibility Report. Target end of January, 2019. • Initiate Options Analysis. Target end of February. | Green |  | On Track
Project Cipher |  |  |  | R1. Tight timelines to develop model and detect signals R2. Data overfitting (volume) |  | • Pending deliberation from DM - Approved • Data deep dive and contextualization with assigned inspector (Justin Budgell) • Development of model • Chieu to provide data support, Malek to observe and co-develop for future scaling and expansion of model • Feasibility Analysis from Cipher | Green |  | On Track

## Description
Project Descriptions
IP/IT# | Project | Description | Deliverables | Planned.Start | Planned.End | Actual.Start | Actual.End | % Complete | Schedule.Health
103 | Single Window Initiative | Sustaining activities related to evolving import requirements. Regulatory, program, and technical changes at CBSA may necessitate periodic enhancements to the SWI application. | Project Close-out (DG-IP) | 2017-08-01 | 2018-03-31 | 2018-08-01 | 2019-01-11 | 100 | 6+ Months
|  |  | Project Close-out (EC-FIPT) | 2017-08-01 | 2018-03-31 | 2018-08-01 |  | 90
435 | Drug Shortages | This project established a contract with an independent third party to develop, implement, and maintain a drug shortage reporting system in support of mandatory drug shortage and discontinuation reporting. Priorities for the coming years focus around providing tools to assist with compliance and enforcement activities. | R2.2 Phase 2 | 2018-10-17 | 2018-10-24 | 2018-07-24 | 2018-10-24 | 100 | No Change
|  |  | R2.3 Development | 2018-10-01 | 2018-11-09 | 2018-10-01 | 2018-11-23 | 100 | 12
|  |  | R2.3 UAT & Bug fixes | 2018-11-26 | 2018-12-10 | 2018-11-26 | 2018-12-06 | 100 | Early
|  |  | R2.3 Communication | 2018-11-19 | 2018-12-18 | 2018-11-06 | 2018-12-18 | 100 | No Change
|  |  | R2.3 Production Release | 2018-12-18 | 2018-12-18 | 2018-12-19 | 2018-12-19 | 100 | No Change
|  |  | R2.4 Business Requirements | 2018-11-01 | 2018-11-19 | 2018-11-01 | 2018-11-30 | 100 | No Change
|  |  | R2.4 Development | 2019-01-07 | 2019-03-15 | 2019-01-21 |  | 60
|  |  | R2.4 UAT & Bug Fixes | 2019-03-18 | 2019-03-29 | 2019-02-15 |  | 50
|  |  | R2.4 Communication | 2019-03-29 | 2019-03-29
|  |  | R2.4 Production Release | 2019-03-31 | 2019-03-31
|  |  | R2.4 Demo to stakeholders | 2019-04-10 | 2019-04-10
628 | Establishment Licensing and Inspections | There are a number of different post-market programs at Health Canada that authorize applicants to conduct regulated activities, against regulated products, at specific locations. These include: • Medical Device Establishment Licensing (RORB) • Natural Health Product Site Licensing (HPFB) • Controlled Substances Dealer Licensing (HECSB) • Drug Establishment Licensing (RORB) There are two active IP projects (CSPS and e-CES) that include this functionality. It is also expected that the Cannabis legalization program will require this functionality. Most programs in this space are using systems with growing aging IT risks, or are still having to use paper and spreadsheet based processes. Intended direction is to identify and acquire a highly configurable COTS product that is targeted at the regulatory licensing space. This solution will be available to all programs as their primary option for this capability. Functionality that is within scope of solution is: • application intake, review, and triage • inspections that support licence decisions • risk assessment • decision workflow • license/permit generation and notification • calculation & collection of license fees (cost recovery) | Complete options analysis & have business case DG/ADM approved | 2017-09-08 | 2017-11-17 | 2017-09-08 | 2018-06-14 | 100 | 3-6 Months
|  |  | Business Case DG/ADM approved | 2017-09-08 | 2017-11-17 | 2018-04-24 | 2018-12-18 | 100 | 6+ Months
|  |  | Project Charter DG/ADM approved | 2017-09-08 | 2017-11-17 | 2017-11-01 | 2018-12-18 | 100 | 6+ Months
|  |  | Complete preliminary PCRA | 2017-09-08 | 2017-11-17 | 2018-09-11 | 2018-09-11 | 100 | 6+ Months
|  |  | Complete stage 2 costing | 2017-09-08 | 2017-11-17 | 2018-06-14 | 2018-10-01 | 100 | 6+ Months
|  |  | DG-IP Gate 2 Review | 2017-09-08 | 2017-12-09 | 2018-12-01 | 2018-12-18 | 100 | 6+ Months
|  |  | EC-FIPT Gate 2 Approval | 2017-09-08 | 2017-12-09 | 2019-01-16 | 2019-01-16 | 100 | 6+ Months
|  |  | Procurement Management Plan | 2019-01-16 | 2019-03-31
|  |  | Privacy Plan | 2019-01-16 | 2019-03-31 | 2019-01-16 |  | 90
|  |  | Finalise the High Level Functional Requirements | 2019-01-16 | 2019-03-31 | 2019-01-16 |  | 40
|  |  | Information Architecture | 2019-01-16 | 2019-03-31 | 2019-02-18 |  | 10
|  |  | Components Interoperability Requirements | 2019-01-16 | 2019-03-31
|  |  | High Level Solution Architecture and Design | 2019-01-16 | 2019-03-31
A01 | ROEB Data Analytics & Business Solutions | There will be multiple sub-projects under Data Analytics and Business Solutions but DABS also has operaetional activities, with key priorities include ensuring appropriate IT tools and infrastructure and enhanced capacity though skills and talent development that will be ongoing in perpetuity. This will drive business stabilization, transformation and modernization across multiple areas in the branch and improve decision-making through new insights. In the near term, a focus on data quality, implementation of a data management and data governance framework, and stabilizing and enhancing existing systems will help to improve RORB performance in the sort-run. Longer-term the development of data analytics and business analysis tools and more robust data will allow RORB to be better able to proactively analyze trends to guide our evolving program and effective risk management. The creation of a Community of Practice within the branch will provide support and best practices. SAS is the departmental standard for business analysis and statistical reporting. RORB will be acquiring SAS licences in support of business analysis/risk-intelligence projects. IMSD has two priorities for SAS 1) secure funding for the stabilization of the SAS Enterprise Guide environment (statistical reporting tools); and 2) preparing HC for the longer-term alignment and onboarding with the GoC SAS Enterprise solution. | Branch IT assessment | 2019-10-01 | 2020-06-30 | 2019-10-01 |  | 60
|  |  | ROEB data literacy program | 2019-10-01 | 2021-06-30 | 2019-10-01 |  | 20
|  |  | Branch data analytics policy | 2019-10-01 | 2020-12-31 | 2019-10-01 |  | 30
|  |  | Data inventory | 2019-10-01 | 2021-06-30 | 2019-10-01 |  | 20
|  |  | Improving hardware & data science environment | 2020-04-01 | 2020-12-31
|  |  | Project Cipher deliverables | 2019-10-01 | 2021-06-30 | 2019-10-01 |  | 20
|  |  | Project Cyclops deliverables | 2019-10-01 | 2021-06-30 | 2019-10-01 |  | 20
|  |  | Use case: EHP PMF | 2019-10-01 | 2021-03-31 | 2019-10-01 |  | 25
|  |  | Use case: Drug analysis | 2019-10-01 | 2020-09-30 | 2019-10-01 |  | 40
|  |  | PSES dashboard | 2019-10-01 | 2021-06-30 | 2019-10-01 |  | 20
|  |  | Strategic roadmap (DASR) for 2020/21 | 2020-01-01 | 2020-03-31 | 2020-01-01 |  | 80
A02 | ROEB Electronic Licensing and Global Supply Chain Mapping | Develop a holistic and comprehensive view of Canada’s pharmaceutical global supply chain in an effective and efficient manner to: - Support evidence-based regulatory decisions-making and supporting both strategic and regulatory policy direction; - Better inform our compliance and enforcement priorities and actions based on analytics and reporting using evidence based risk evaluations. | Pitch to Directors | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-02-07 | 100 | No Change
|  |  | Identify program SMEs | 2019-02-07 | 2019-02-19 | 2019-02-07 |  | 10
|  |  | Whiteboard sessions for requirements gathering | 2019-03-04 | 2019-03-04
|  |  | Questionnarie completed | 2019-03-13 | 2019-03-13
|  |  | Draft requirements and use cases | 2019-03-04 | 2019-03-29
|  |  | Appoval of requirements | 2019-04-12 | 2019-04-12
A03 | Enabling Compliance and Enforcement Program Delivery | To enable RORB to better support enhanced efficiency and effectiveness in Compliance and Enforcement program delivery investments will be made in learning management, inspection scheduling, assisted human reproduction, fleet, client service tools, and Infrastructure and Software as a Service. | Pilot LMS: Cannabis | 2018-07-01 | 2018-12-31 | 2018-07-01 |  | 95
|  |  | Pilot JIRA: First 3 instances (DEL, Border, AMS) | 2018-09-01 | 2019-01-01 | 2018-09-01 |  | 75
|  |  | Pre-build activities - LMS: Health Product Inspection and Licensing | 2018-12-01 | 2018-12-16 | 2018-12-01 | 2019-02-15 | 100 | No Change
|  |  | Pre-build activities - LMS: Tobacco & Vaping | 2018-11-01 | 2018-11-16 | 2018-11-01 | 2018-11-16 | 100 | No Change
|  |  | Build activities - LMS: Tobacco & Vaping | 2018-11-16 | 2019-01-04 | 2018-11-16 |  | 65
|  |  | Jira to Production | 2019-03-07 | 2019-03-30 | 2019-03-01 |  | 5
|  |  | Pre-build activities - JIRA: Controlled Substances | 2019-03-11 | 2019-04-01
A04 | ROEB Aging IT (Stabilization/Modernization/Transformation) | There are 28 RORB IT solutions that are considered Aging IT. Systems will be addressed by priority and grouped with projects of similar priority. There are 28 RORB IT solutions that are considered aging IT. RORB will conduct a review of aging IT systems and produce a plan to remediate through tolerating, migrating, innovating, or eliminating these systems. High priority systems under aging IT include: Inspection Reporting System, Incident System, Export Certificate Database, and the Laboratory Information Management System. | Windows 2008 server migration | 2018-07-15 | 2018-12-31 | 2018-08-06 |  | 60
|  |  | Decommission applications | 2018-04-01 | 2019-03-31
|  |  | APM Update for Business Applications | 2018-11-01 | 2018-11-13 | 2018-11-01 |  | 15
A05 | Drug and Health Product Inspections Database | As part of the regulatory transparency priority, seven different programs make use of the online Inspection Database to post their inspection reports to the Healthy Canadians website, where the public has access to them. There are requirements to update this database and improve the functionality of the website as well as expand the amount of information available. | Cloud Environment | 2018-05-15 | 2019-03-31 | 2018-05-15 |  | 50
|  |  | Enhancement Phase 1 | 2018-04-01 | 2019-03-31 | 2018-04-01 |  | 80
|  |  | API (GMP, GVP, Blood) | 2018-04-01 | 2019-03-31 | 2018-06-01 |  | 80
|  |  | API (MD, CT, CTO, DS) | 2018-11-26 | 2019-03-31 | 2018-11-26 |  | 40
A06 | Modernizing the RORB Employee eToolkit | This project focuses on providing off-the-shelf hardware and software solutions to employees working in the RORB program to modernize the workforce and enable a seamless transition from office to the field. It addresses challenges in the technology currently made available to RORB employees and proposes alternative solutions that would allow them to do their jobs more efficiently. | Smartphones for MDIU pilot group to replace BB Leaps, where requested (20) | 2018-08-17 | 2018-10-01 | 2018-08-27 | 2018-09-18 | 100 | Early
|  |  | Training for MDIU Pilot group | 2018-05-01 | 2018-05-31 | 2018-05-24 | 2018-05-24 | 100 | Early
|  |  | Survey MDIU pilot group for feedback on devices and training | 2018-07-01 | 2018-09-02 | 2018-07-01 | 2018-09-02 | 100 | No Change
|  |  | Aquire tablets/smartphones (ROEB) | 2018-07-15 | 2019-04-01 | 2018-07-30 |  | 85
|  |  | Mobile Technology Training (ROEB) | 2018-10-31 | 2019-04-01 | 2018-10-31 |  | 75
|  |  | Virtual Workstation Pilot (HPC, TVC) | 2018-10-31 | 2019-01-01 | 2018-10-31 |  | 25
|  |  | E-Post connect onboarding and training (ROEB) | 2018-04-01 | 2019-03-01 | 2018-04-01 | 2019-02-28 | 100 | Early
|  |  | Smartpen Pilot (CSP) | 2019-01-01 | 2019-07-01 | 2019-01-15 |  | 10
701 | Border Compliance IT Modernization | Invest in a modern IM/IT system for the Health Products Border Program to bring their data collection and management processes onto a single mobile platform, with the following key features: • Workload management • Process standardization • Data quality and structure • Enterprise collaboration • Reporting This IT system will replace two Lotus Notes databases and numerous Excel spreadsheets being used by the health products border program. This initiative is closely linked with Business Analysis/Risk Intelligence initiatives outlined above. | Gate 3 planning & approval | 2018-07-23 | 2018-10-15 | 2018-11-28 | 2019-02-21 | 100 | 3-6 Months
|  |  | Project Management Plan | 2018-11-28 | 2019-01-15 | 2018-11-28 | 2019-01-31 | 100 | No Change
|  |  | Project Complexity and Risk Assessment | 2018-11-28 | 2019-01-15 | 2018-11-28 | 2019-01-31 | 100 | No Change
|  |  | Refined Cost Estimates | 2018-11-28 | 2019-01-15 | 2018-11-28 | 2019-02-08 | 100 | No Change
|  |  | High-level Functional Requirements | 2018-11-28 | 2019-01-15 | 2018-11-28 | 2019-01-31 | 100 | No Change
|  |  | Security Documents (Statement of Sensitivity, Security Assessment and Authorization Report, Privacy Impact Assessment) | 2018-11-28 | 2019-01-15 | 2018-11-28 | 2019-01-15 | 100 | No Change
|  |  | Gate 3 Deck | 2018-01-15 | 2019-01-21 | 2019-01-15 | 2019-02-08 | 100 | No Change
Sytem Procurement & Customization
|  |  |  | 2018-10-02 | 2019-06-01 | 2019-01-24 | 2019-06-01 | 100 | No Change
704 | Quality Management System | System for Quality Management (ISO 9001:2000): is part of a suite of databases designed specifically to meet the requirements of ISO 9001:2000, the QSI System for Quality Management helps an organization reap the benefits of ISO certification, including improved customer satisfaction and reduced costs. QSi, the software suite used to manage a Quality Management System (QMS) is currently unsupported and is housed on an Aging IT Platform (Lotus Notes). The software suite is inherently unstable and contains many bugs. The RORB programs using QSi (Labs, HPCD, MDCCD) are concerned of a system collapse and how it could potentially impact current Accreditation and Mutual Recognition Agreements in place. | Gate 2 - Project Initiation
|  |  | HLBRD | 2018-10-01 | 2018-11-18 | 2018-09-02 | 2019-01-15 | 100 | No Change
|  |  | Business Case / Project Charter / Project Schedule | 2018-09-01 | 2019-01-11 | 2018-09-28 |  | 85
|  |  | Options analysis | 2018-11-18 | 2019-03-01 | 2019-01-16
|  |  | IT Solution Recommendation | 2019-01-11 | 2019-03-01
|  |  | Pre-DG IP Review | 2019-04-01 | 2019-04-01
|  |  | Gate 2 DG-IP Recommendation | 2019-04-01 | 2019-04-01
|  |  | EC-FIPT Approval | 2019-04-01 | 2019-04-01
|  |  | Gate 3- Project Planning | 2019-04-01 | 2019-07-01
|  |  | Gate 4- Project Execution | 2019-08-01 | 2020-06-01
|  |  | Gate 5- Project Close-Out | 2020-06-01 | 2020-09-01
A07 | GCdocs Project | The objective of the RORB GCdocs Project is to support the IMSD GCdocs implementation plan and to prepare RORB for the deployment of the GCdocs tool. The RORB plan is critically dependent on IMSD timelines. The ultimate goal is for a smooth transition to GCdocs within RORB. To ensure this, RORB desired outcomes include: • RORB staff are aware of the GCdocs initiative • RORB managers and staff are aware of the benefits of using GCdocs in meeting their IM obligations • RORB managers and staff know how to use the basic features of GCdocs in their everyday work • GCdocs is configured to meet the requirements of RORB and the transition to GCdocs is smooth • RORB BIMA and IM staff are able to provide day-to-day GCdocs user support and to escalate technical issues as required The objective of the RORB GCdocs Project is to support the IMSD GCdocs implementation plan and to prepare RORB for the deployment of the GCdocs tool. The RORB plan is critically dependent on IMSD timelines. The ultimate goal is for a smooth transition to GCdocs within RORB. To ensure this, RORB desired outcomes include: • RORB staff are aware of the GCdocs initiative • RORB managers and staff are aware of the benefits of using GCdocs in meeting their IM obligations • RORB managers and staff know how to use the basic features of GCdocs in their everyday work • GCdocs is configured to meet the requirements of RORB and the transition to GCdocs is smooth • RORB BIMA and IM staff are able to provide day-to-day GCdocs user support and to escalate technical issues as required The objective of the RORB GCdocs Project is to support the IMSD GCdocs implementation plan and to prepare RORB for the deployment of the GCdocs tool. The RORB plan is critically dependent on IMSD timelines. The ultimate goal is for a smooth transition to GCdocs within RORB. To ensure this, RORB desired outcomes include: • RORB staff are aware of the GCdocs initiative • RORB managers and staff are aware of the benefits of using GCdocs in meeting their IM obligations • RORB managers and staff know how to use the basic features of GCdocs in their everyday work • GCdocs is configured to meet the requirements of RORB and the transition to GCdocs is smooth • RORB BIMA and IM staff are able to provide day-to-day GCdocs user support and to escalate technical issues as required | Preparatory Phase | 2018-05-01 | 2018-12-31
|  |  | Conduct an online scan for GCdocs information | 2018-05-01 | 2018-12-31 | 2018-05-01 | 2018-12-31 | 100 | No Change
|  |  | Develop RORB communication packages to raise awareness and promote training | 2018-06-04 | 2018-11-30 | 2018-06-04 |  | 80
|  |  | GCdocs training for TBI-IM staff | 2018-07-03 | 2018-11-30 | 2018-07-03 |  | 50
|  |  | Review Directorate RKAI’s for accuracy and completeness | 2018-07-03 | 2018-08-31 | 2018-07-03 | 2018-09-28 | 100 | No Change
|  |  | Develop RORB GCdocs support and issues management documents | 2018-09-10 | 2018-12-31 | 2018-09-10 | 2019-01-14 | 100 | No Change
|  |  | Mobilization Phase | 2018-07-09 | 2019-01-31
|  |  | Establish high level folder structure of GCdocs (with BIMA) | 2018-07-09 | 2018-08-31 | 2018-07-09 | 2019-01-10 | 100 | 3-6 Months
|  |  | Establish GCdocs working group consisting of Directorate SMEs within RORB | 2018-08-01 | 2018-08-31 | 2018-08-01 | 2018-08-31 | 100 | No Change
|  |  | Establish low level folder structure of GCdocs (with Branch SME working groups) | 2018-09-10 | 2018-11-30 | 2018-10-11 | 2018-12-14 | 100 | No Change
|  |  | Establish Branch membership (folder access) structure | 2018-09-10 | 2018-11-30 | 2019-01-11
|  |  | All staff training: GCdocs e-learning course “GCdocs Fundamentals” | 2018-10-01 | 2019-01-31 | 2019-12-18
|  |  | Validation of GCdocs folder structure and folder access | 2018-11-19 | 2018-11-30 | 2019-01-11
|  |  | Implementation Phase | 2019-02-05 | 2019-02-26
|  |  | Participate in deploying GCdocs tool to RORB workstations | 2019-02-05 | 2019-02-12
|  |  | Execute support and issues management protocol | 2019-02-05 | 2019-02-12
|  |  | All staff training: GCdocs e-learning course “Unleash the Power of GCdocs” | 2019-02-12 | 2019-02-26
705 | DAS Modernization | Modernization of the DAS Labs business proecess and introduction of an end-to-end IT solution for the submission, triage, assessment, and issuance of the DAS Certificate of Analysis. Modernization of the DAS Labs business proecess and introduction of an end-to-end IT solution for the submission, triage, assessment, and issuance of the DAS Certificate of Analysis. | Gate 1 Deck | 2018-10-01 | 2018-11-01 | 2018-10-01 | 2019-01-10 | 100 | No Change
|  |  | Process Mapping | 2018-11-01 | 2018-12-01 | 2018-11-01 | 2019-01-11 | 100 | No Change
|  |  | Costing | 2018-10-01 | 2018-12-01 | 2018-10-01 |  | 25
|  |  | Gate 1 Approval | 2018-11-30 | 2018-11-30 | 2018-11-30 | 2019-01-11 | 100 | No Change
|  |  | High Level Requirements | 2018-11-01 | 2019-02-08 | 2019-01-14 |  | 70
|  |  | Project Charter | 2019-01-14 | 2019-01-25 | 2019-01-21 |  | 90
|  |  | OA | 2019-02-11 | 2019-03-15 | 2019-02-22 |  | 10
|  |  | PCRA | 2019-03-01 | 2019-03-08 | 2019-02-21 | 2019-02-21 | 100 | Early
A09 | Cost Recovery | Providing data and analytics support to Cost Recovery by: •analyzing and validating eCES is available and adequate to support the new fee structure •developing reports and datasets for ALR and fee calculationsand •analyzing and validating DELU's new process and workflow data to ensure alignment with the new CR policy and fee structure •developing a Pause-the-Clock Algorithm under DELU's new workflowsProviding data and analytics support to Cost Recovery by: •analyzing and validating eCES is available and adequate to support the new fee structure •developing reports and datasets for ALR and fee calculationsand •analyzing and validating DELU's new process and workflow data to ensure alignment with the new CR policy and fee structure •developing a Pause-the-Clock Algorithm under DELU's new workflows | CR reports for HPIL | 2018-10-29 | 2018-01-31 | 2018-10-29
|  |  | Analysis and validation report of Table A data entry test | 2018-10-29 | 2018-12-15
|  |  | Datasets for fee calculator | 2018-10-29 | 2018-01-31 | 2018-10-29
|  |  | Analysis and validation report of HPIL's new workflows | 2018-10-29 | 2019-01-31
|  |  | Pause-the-Clock algorithm | 2018-01-02 | 2019-03-31
SF2018/19-007 | Project Cyclops | The project is proposing to create a new process enabled by a digital-tool (smartphone camera / wearable device) to virtualize optically represented text on the label, query the data via existing databases, identify and highlight instances of non-compliances, and visually depict the issue by overlaying the information back on to the camera/device feed. This will allow Inspectors to review the labels on-site, without the need to collect samples and invest more time into the inspection. As a small scale proof of concept, a solution can be developed using the minimal viable product model for Natural Health Products and targeted for Inspectors in the Health Product Compliance and the Border Integrity Unit for testing.The project is proposing to create a new process enabled by a digital-tool (smartphone camera / wearable device) to virtualize optically represented text on the label, query the data via existing databases, identify and highlight instances of non-compliances, and visually depict the issue by overlaying the information back on to the camera/device feed. This will allow Inspectors to review the labels on-site, without the need to collect samples and invest more time into the inspection. As a small scale proof of concept, a solution can be developed using the minimal viable product model for Natural Health Products and targeted for Inspectors in the Health Product Compliance and the Border Integrity Unit for testing. | Environmental Scan | 2018-11-15 | 2019-01-09 | 2018-11-15 | 2019-02-15 | 100 | No Change
|  |  | Options Analysis for MVP | 2019-01-09 | 2019-05-10 | 2019-02-15 | 2019-05-10 | 100 | No Change
|  |  | Final Recommended on MVP Solution | 2019-05-10 | 2019-06-03 | 2019-05-10 | 2019-06-03 | 100 | No Change
| Gadget Phase I | Utilizing automation and blockchain improve the existing HC owned Offsite Inspection Process in collaboration with National Research Council (NRC) . While HC provides the regulatory business case, NRC provides the technical expertise to advance their research. | Deliver proof of concept of initial proposed system | 2018-05-01 | 2019-03-31
|  |  | Construct initial project goals after collaboration with NRC | 2018-06-15 | 2018-07-16
|  |  | Create a minimum viable product mock up and build pipeline | 2018-07-16 | 2018-08-17
|  |  | Design a Domain Model, Basic process models, Enable HTTPS | 2018-08-07 | 2018-08-17
|  |  | Conceptualize MVP and create sample UI pages | 2018-08-27 | 2018-09-07
|  |  | Code Production | 2018-10-08 | 2018-10-19
Design Template Deliverable from Graphics Designer
Cut Images from CSS Cutter
Add cut images into the template
| Hummingbird | Using Unmanned Aerial Systems (UAS) create a new outdoor inspection system to positively impact the operational activities of inspectors. Initial focus is to achieve benefit to inspectors within Cannabis, Controlled Substances (Opium Poppy), and Pesticide programs. The major goals of the project include: • Identify, address and fill the gaps within the current limitations in the field. • Provide inspectors with more accurate and modernized tools. • Ensure better safety for inspectors. • Utilize the vast data collected through Unmanned Aerial Vehicles (UAV) to aid inspectors in real time inspections as well as help Health Canada better understand non-compliance patterns and loopholes. | Submit Solution Fund Stream I proposal |  | 2018-10-01
|  |  | Gather Key Business Requirements and Features for MVP |  |  |  | 2019-01-25 | 100
|  |  | Develop Feasibility Report |  | 2019-01-31
|  |  | Initiate Options Analysis |  | 2019-02-28
|  |  | Deliver feasibility and options report |  | 2019-03-31
| Cipher | This project will serve as a vehicle for Health Canada to explore and experiment with text mining, natural language processing, machine learning and artificial intelligence to mine inspection reports for insight and actionable information that would support prospective and predictive analysis. The project goals are: • Assess RORB’s inspection reports • Assess text mining and natural language processing algorithms and methods; develop a small-scale experimental model • Assess machine learning and AI algorithms and methods; develop a small-scale experimental model The success of the project will decipher caches of unstructured information within inspection reports for analytical and data enrichment purposes, that would support decision making. | Submit Solution Fund Stream I proposal |  | 2018-10-01
Gather Key Business Requirements and Features for MVP
|  |  | Data Assessment |  | 2019-03-22
|  |  | Text Mining and NLP Assessment |  | 2019-04-01
|  |  | Machine Learning and AI Assessment |  | 2019-06-28
Formulas:
Schedule.Health = IF(OR([Actual.End]="",[Planned.End]=""),"",IF([Actual.End]<[Planned.End],"Early",IF(DATEDIF([Planned.End],[Actual.End],"M")<3,"No Change",IF(DATEDIF([Planned.End],[Actual.End],"M")<=6,"3-6 Months","6+ Months"))))

## Budget
Budget ($ in 000s)
IP# | Project | Type | Budget | Actuals | Commitment | Anticipated | Total Forecast | Variance | Notes
103 | Single Window Initiative | Salary | 20 | 20 |  |  | 20 | 0 | Salary for project close-out activities will be fully spent this fiscal.
|  | O&M | 0 |  |  |  | 0 | 0
|  | Total | 20 | 20 | 0 | 0 | 20 | 0
628 | Establishment Licensing and Inspections | Salary | 200 |  |  |  | 0 | 200 | Must tap into DM reserve for project funding
|  | O&M | 260 |  |  |  | 0 | 260
|  | Total | 460 | 0 | 0 | 0 | 0 | 460
435 | Drug Shortages | Salary | 25 | 25 |  |  | 25 | 0
|  | O&M | 255 | 255 |  |  | 255 | 0 | Enhancements + Hosting. Contract period ends June 30, 2019
|  | Total | 280 | 280 | 0 | 0 | 280 | 0
A01 | ROEB Data Analytics & Business Solutions | Salary | 266 |  |  |  | 0 | 266
|  | O&M | 200 | 145 | 35 |  | 180 | 20 | 1. $35K contractor (Martin Blumenauer) 2. $110K Gartner contract 3. $35K committed to training DABS FTEs and hardware procurement (e.g. tablets)1. $35K contractor (Martin Blumenauer) 2. $110K Gartner contract 3. $35K committed to training DABS FTEs and hardware procurement (e.g. tablets)1. $35K contractor (Martin Blumenauer) 2. $110K Gartner contract 3. $35K committed to training DABS FTEs and hardware procurement (e.g. tablets)
|  | Total | 466 | 145 | 35 | 0 | 180 | 286
A02 | ROEB Electronic Licensing and Global Supply Chain Mapping | Salary | 50 | 40 |  | 10 | 50 | 0
|  | O&M | 0 |  |  |  | 0 | 0 | Need to add Peter B time here
|  | Total | 50 | 40 | 0 | 10 | 50 | 0
A03 | Enabling Compliance and Enforcement Program Delivery | Salary | 45 |  |  |  | 0 | 45
|  | O&M | 40 |  |  |  | 0 | 40 | Not using Enterprise version of Edubrite, cost is ~$10KCAD JIRA licences are $24K USD = ~$30K CADNot using Enterprise version of Edubrite, cost is ~$10KCAD JIRA licences are $24K USD = ~$30K CADNot using Enterprise version of Edubrite, cost is ~$10KCAD JIRA licences are $24K USD = ~$30K CAD
|  | Total | 85 | 0 | 0 | 0 | 0 | 85
A04 | ROEB Aging IT (Stabilization/Modernization/Transformation) | Salary | 50 |  |  |  | 0 | 50
|  | O&M | 0 |  |  |  | 0 | 0
|  | Total | 50 | 0 | 0 | 0 | 0 | 50
A05 | Drug and Health Product Inspections Database | Salary | 0 |  |  |  | 0 | 0
|  | O&M | 0 |  |  |  | 0 | 0
|  | Total | 0 | 0 | 0 | 0 | 0 | 0
A06 | Modernizing the ROEB Employee eToolkit | Salary | 90 | 85 |  | 5 | 90 | 0
|  | O&M | 463 | 459 | 261 |  | 720 | -257 | Extra Commitments: $94,442.48 for 40 tablets and $166, 988 for 218 smartphones, as per ADM request.
|  | Total | 553 | 544 | 261 | 5 | 810 | -257
IP701 | Border Compliance IT Modernization | Salary | 489 |  |  |  | 0 | 489
|  | O&M | 524 |  |  |  | 0 | 524
|  | Total | 1013 | 0 | 0 | 0 | 0 | 1013
IP704 | Quality Management System | Salary | 75 | 45 |  |  | 45 | 30
|  | O&M | 100 | 65 |  |  | 65 | 35
|  | Total | 175 | 110 | 0 | 0 | 110 | 65
A07 | GCdocs Project | Salary | 80 | 0 |  |  | 0 | 80
|  | O&M | 50 |  |  |  | 0 | 50
|  | Total | 130 | 0 | 0 | 0 | 0 | 130
SF2018/19-007 | Project Cyclops | Salary | 60 | 0 |  |  | 0 | 60
|  | O&M | 101 |  |  |  | 0 | 101
|  | Total | 161 | 0 | 0 | 0 | 0 | 161
705 | DAS Modernization | Salary | 0 | 38 |  | 76 | 114 | -114 | Project was not on the original plan for this year so variance will be 100%
|  | O&M | 0 | 25 |  | 55 | 80 | -80 | Martin Blumenauer TA cost ~$80K
|  | Total | 0 | 63 | 0 | 131 | 194 | -194
| Gadget Phase I | Salary
O&M
|  | Total | 0 | 0 | 0 | 0 | 0 | 0
| Hummingbird | Salary | 79.779
|  | O&M | 22 | [5 empty] | Includes only external Professional services needed for Unmanned Aerial Vehicle (UAV)
|  | Total | 101.779 | 0 | 0 | 0 | 0 | 0
| Project Cipher | Salary | 80
|  | O&M | 50
|  | Total | 130 | 0 | 0 | 0 | 0 | 0
[7 empty] | 3268 | 3598

## Risks and Issues
Risks and Issues
IP# | Project | Risks | Issues | Comments
103 | Single Window Initiative | 1. Limited trade uptake poses challenges for benefits realization at time of writing project closeout report. | None | Transfer of OPI responsibilities is complete. Awaiting close out at EC-FIPT
628 | Establishment Licensing and Inspections | 1. Limited IMSC/SSC capacity may negatively impact project timelines 2. Current project would require EARB approval 3. SSC now requires their own PM going through their own gating process for any complex projects. ELIS may fall under that category 4. Potential risk of delays due to election period (if Government announces a budgetary freeze or that the present Minister calls for a stop on all departmental spending) 5. Scarcity in PIA consultant availability may delay deliverable, or may increase budget given the high demand 6. Lean Analysis/Business Transformation resources for MD 7. Contracting vehicles 8. IDMP integration with 628 9. Integration of Prototyping in overall project1. Limited IMSC/SSC capacity may negatively impact project timelines 2. Current project would require EARB approval 3. SSC now requires their own PM going through their own gating process for any complex projects. ELIS may fall under that category 4. Potential risk of delays due to election period (if Government announces a budgetary freeze or that the present Minister calls for a stop on all departmental spending) 5. Scarcity in PIA consultant availability may delay deliverable, or may increase budget given the high demand 6. Lean Analysis/Business Transformation resources for MD 7. Contracting vehicles 8. IDMP integration with 628 9. Integration of Prototyping in overall project
435 | Drug Shortages | 1. The current list of enhancements is being updated frequently as more enhancements are identified through user feedback and use of the site. As such, the roadmap is constantly changing as new enhancements may have a higher priority than existing ones. 2. Project will transfer of ownership to HPCRM, and unknown with project extension and enhancements may not be feasible if there is no program money injected after June 2019.1. The current list of enhancements is being updated frequently as more enhancements are identified through user feedback and use of the site. As such, the roadmap is constantly changing as new enhancements may have a higher priority than existing ones. 2. Project will transfer of ownership to HPCRM, and unknown with project extension and enhancements may not be feasible if there is no program money injected after June 2019. | None
A01 | RORB Data Analytics & Business Analysis | None | None
A02 | Global Supply Chain Mapping + RORB Electronic Licensing | 1. Multiple investments in the licensing and inspection space muddies the decision making process. 2. Multi-branch and multi-program complexity complicates the ability for a solution to meet all indivual business needs. 3. Limited time to engage with industry associations. 4. Limited IMSD/SSC capacity may negatively impact project timelines. 5. Year 1 Comprehensive Review committments may not be met if using IP628 to address some scope items. 6. Undefined business problem makes identifying appropriate solutions difficult1. Multiple investments in the licensing and inspection space muddies the decision making process. 2. Multi-branch and multi-program complexity complicates the ability for a solution to meet all indivual business needs. 3. Limited time to engage with industry associations. 4. Limited IMSD/SSC capacity may negatively impact project timelines. 5. Year 1 Comprehensive Review committments may not be met if using IP628 to address some scope items. 6. Undefined business problem makes identifying appropriate solutions difficult | None | • Project being led by PRSD
A03 | Enabling Compliance and Enforcement Program Delivery | 1. Technical: Engage IMSD/SSC in advisory committee. Ensure appointment of technically qualified team. 2. Resources: Engagement with programs to ensure availability of SMEs as required for each sub-project. 3. Uncertainties: Ensure linkages and awareness of larger investment plans across the Branch to be able to shift priorities accordingly. Linkages between systems (Jira and Outlook) may result in compatibility issues. 4. Hosting: Coordination with IMSD to resolve hosting environments for test, dev, prod.1. Technical: Engage IMSD/SSC in advisory committee. Ensure appointment of technically qualified team. 2. Resources: Engagement with programs to ensure availability of SMEs as required for each sub-project. 3. Uncertainties: Ensure linkages and awareness of larger investment plans across the Branch to be able to shift priorities accordingly. Linkages between systems (Jira and Outlook) may result in compatibility issues. 4. Hosting: Coordination with IMSD to resolve hosting environments for test, dev, prod. | None
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | R1. Competing priorities within IMSD, SSC and business groups could delay work R2. Volume of work may increase and cause workload issuesR1. Competing priorities within IMSD, SSC and business groups could delay work R2. Volume of work may increase and cause workload issues | None | Typically find ourselves in a reaction position to requests from IMSD and SSC, whereby they are given a priority and we are expected to comply.
A05 | Drug and Health Product Inspections Database | 1. Resource intensive for both IMSD and SME. | I1. Changes to DHPID will be required for next FY due to implementation of AHRA, as well as new MD action plan. The scope of these changes is unknown, as such the impacts and cost are unknown. I2. Due to delays with Cloud and middleware teams, the Cloud production deployment will not meet MArch 31st deadline.I1. Changes to DHPID will be required for next FY due to implementation of AHRA, as well as new MD action plan. The scope of these changes is unknown, as such the impacts and cost are unknown. I2. Due to delays with Cloud and middleware teams, the Cloud production deployment will not meet MArch 31st deadline. | Cloud process taking longer than anticipated as IMSD sorts out the process.
A06 | Modernizing the RORB Employee eToolkit | 1. The software solutions required for inspections are not compatible with the Surface Pro tablet or smartphone 2. Industry may be resistant to uploading their data into the cloud (epost Connect) 3. Inspectors continue to use other means to transfer data as epost Connect is difficult to use 4. Insufficient funding for Phase II of the project and delivery to other programs 5. The e-signature is not legally supported. 1. The software solutions required for inspections are not compatible with the Surface Pro tablet or smartphone 2. Industry may be resistant to uploading their data into the cloud (epost Connect) 3. Inspectors continue to use other means to transfer data as epost Connect is difficult to use 4. Insufficient funding for Phase II of the project and delivery to other programs 5. The e-signature is not legally supported. | 1. The contact for PWGSC provided for validation of esignautres is not valid anymore. 2. The BB Leaps delivered by SSC are not compatible with the Bell Network for data usage and rely on their backup network. 3. Imaging SPs centrally to be sent to Inspectors is more costly than anticipated because of the value of the goods when shipping. 4. GMP procured their own tablets, outside of the project, but require support/training. 5. Canada Post slow to respond to requests for additional info regarding e-post connect, for IT security to complete their assessment. 1. The contact for PWGSC provided for validation of esignautres is not valid anymore. 2. The BB Leaps delivered by SSC are not compatible with the Bell Network for data usage and rely on their backup network. 3. Imaging SPs centrally to be sent to Inspectors is more costly than anticipated because of the value of the goods when shipping. 4. GMP procured their own tablets, outside of the project, but require support/training. 5. Canada Post slow to respond to requests for additional info regarding e-post connect, for IT security to complete their assessment. | 1. 2nd phase and future shipments are being directed to users and imaged regionally. 2. GMP provided work instructions and links to resources, and TBI will provide training session. 3. Currently using e-post under Interim Authority to Operate from IT Security. Working with IT Security to gain the necessary info from Canada Post to complete the assessment. 1. 2nd phase and future shipments are being directed to users and imaged regionally. 2. GMP provided work instructions and links to resources, and TBI will provide training session. 3. Currently using e-post under Interim Authority to Operate from IT Security. Working with IT Security to gain the necessary info from Canada Post to complete the assessment.
IP701 | Border IM/IT Modernization | 1. Novel software implementation for GoC. It could therefore result in installation and configuration delays. 2. Partners want scope change 1. Novel software implementation for GoC. It could therefore result in installation and configuration delays. 2. Partners want scope change | 1. Gate 3 delayed till March to harness synergies with IP603, by sharing hosting environment and development costs. | • Gate 2 EC-FIPT approval obtained on Nov 29th. • Stage 3 Kick-Off on Nov 13th. • Detailed BRD and PMP feedback received. • PIA work initated. • Gate 3 delayed till March to allign with IP603 costing requirements.• Gate 2 EC-FIPT approval obtained on Nov 29th. • Stage 3 Kick-Off on Nov 13th. • Detailed BRD and PMP feedback received. • PIA work initated. • Gate 3 delayed till March to allign with IP603 costing requirements.
IP704 | Quality Management System | 1. Multi-branch and multi-program complexity complicates the ability for a solution to meet all indivual business needs (HPFB, HECSB, RORB). 2. Limited IMSD/SSC capacity may negatively impact project timelines (OA completion etc). 3. Timelines are at risk due to late start of the HLBRD Review and OA initiation. All lead time has been diminised and now timelines are at risk of Gate 2 delay. 1. Multi-branch and multi-program complexity complicates the ability for a solution to meet all indivual business needs (HPFB, HECSB, RORB). 2. Limited IMSD/SSC capacity may negatively impact project timelines (OA completion etc). 3. Timelines are at risk due to late start of the HLBRD Review and OA initiation. All lead time has been diminised and now timelines are at risk of Gate 2 delay. | 1. Bugs and Issues are causing certain programs to worry about upcoming audits (MRA implications). For example, the GMP inspection program is to be audited in the Fall of 2018 and requires a fully functional QMS or at least the proposal that a QMS platform is being assessed and / or replaced. | • HLBRD and Project Charter Final Drafts sent to IMSD and OA Team for review and initiation of OA process. • OA initiation on January 16 2019 (following peer review). • OA lead to provide evaluation criteria and list of potential vendors by February 1 2019 (demos to be set shortly after). • First draft of OA to be completed by end of February 2019. • Continue to work on other Gate 2 artifacts ( Business Case, PCRA, Costing Model, Project Plan etc) to both help supplement OA and to line up program and gov. approval. • HLBRD and Project Charter Final Drafts sent to IMSD and OA Team for review and initiation of OA process. • OA initiation on January 16 2019 (following peer review). • OA lead to provide evaluation criteria and list of potential vendors by February 1 2019 (demos to be set shortly after). • First draft of OA to be completed by end of February 2019. • Continue to work on other Gate 2 artifacts ( Business Case, PCRA, Costing Model, Project Plan etc) to both help supplement OA and to line up program and gov. approval.
A07 | GCdocs Project | 1. Inability to configure a common folder structure across all the regulatory branches that takes into account all the common regulatory business processes. 2. Limited IMSD capacity and inadequate planning negatively impacting RORB project timelines and deliverables. 3. Poor engagement from program areas and/or the absence of proper representation (identified SMEs) in the information architecture working group sessions. 4. Multi-branch and multi-program complexity complicates the ability for an enterprise solution that meets all indivual program needs. | 1.Various systems and databases currently being used to store information will need to be granted exemptions. 2. Feasibility of using GCdocs to view and store media files (i.e. videos) in the long-term.
705 | DAS Modernization | R1. Security assessment may limit the technology options available for the project. R2. Procurement of suitable COTS R3. Containment of costs R4. Sources of funding not yet identified. R5. Scope expansion to include all current LIMS programs as part of an enterprise approachR1. Security assessment may limit the technology options available for the project. R2. Procurement of suitable COTS R3. Containment of costs R4. Sources of funding not yet identified. R5. Scope expansion to include all current LIMS programs as part of an enterprise approach | None | • HLBRD and Charter slightly delayed due to late Gate 1 approval • Sources of funding are TBD but costs have been identified at +-100%• HLBRD and Charter slightly delayed due to late Gate 1 approval • Sources of funding are TBD but costs have been identified at +-100%
| Project Cyclops | R1. Inability to find the right technical resources to develop the solution model. R2. Inability to find the right subject matter experts to support the assessment of the solution. R3. Technology required for solution may not be appropriate or ready in the current environment. R4. Current HC infrastructure may not support the interfacing required for the solution(s) available.R1. Inability to find the right technical resources to develop the solution model. R2. Inability to find the right subject matter experts to support the assessment of the solution. R3. Technology required for solution may not be appropriate or ready in the current environment. R4. Current HC infrastructure may not support the interfacing required for the solution(s) available. | None | • Project kick-off meeting on Nov 13 with programs. • Program and data requirements defined. • Professional services secured, and contract initiated on January 23, 2019.• Project kick-off meeting on Nov 13 with programs. • Program and data requirements defined. • Professional services secured, and contract initiated on January 23, 2019.
A09 | Cost Recovery | R1. Timeliness, quality and procedure of of Table A data entry may impose risks on the development of reports supporting CR. R2. Not having the entirety of Table A data entered prior to the development of CR reports may result in exceptions and outliers not being captured and handled. R3. DELU's workflow changes will result in new data entry proceses in eCES. Since the new workflows have not been piloted, DABS is currently working with hypothetical test data to develop reports, which may not accommodate to all exceptions, oiutliers and nuances. This will have implications on Pause-the-Clock (PTC). R4. There is a risk that DELU will change workflows after initial pilot. | I1. Much of the information required for DABS to provide support requires finalized decisions from HPCD; this includes commitments on procedures and timelines to entire Table A data and finalization and piloting of DELU's new workflows for PTC. I2. DABS will have to analyze DELU's new workflows to develop the PTC algorithm. Although the work can start without real data generated from the new workflows, the PTC algorithm cannot be fully developed and validated without it. I3. DELU has opted out on conducting data quality assessment while conducting Table A data entry, which may have implications on the validation of CR reports being developed. | • Due to extenuating circumstances in HPCD, much of the work to be completed by DABS is hindered from proceeding at full throttle. Therefore, DABS will proceed with an iterative approach to develop with whatever information/confirmations are available in short sprints and looping back to HPCD for more feedback and information in the subsequent cycles to minimize loss of time.
| Gadget Phase I | R1. Continuous Deployment method has been preferred over traditional approach to reduce risk to our business holders but it increases difficulty for developers as system breakage is always remains a possibility. R2. So far Blockchain implementation in government has been very limited. Although it opens up a new avenue to build better trust and transparency with government's stakeholders, such new technology might show scalability problems early on. R3. Drastic change in how internal stakeholders receive and consume inspection data. R4. No dedicated project designer was hired (or planned), this is a risk to project considering visual aspect of the project is the first thing stakeholders judge a project by. | I1. Actual inspection process turned out to be somewhat more complex and resource intensive than expected during planning phase. I2. Team members either being sick or having issues collaborating due to personal/professional commitments. I3. No front-end developer was initially hired, however, NRC recruited a co-op student to help with front-end development. I4. Implementing decentralized file server with Gadget back-end. | • Continous Deployment allows business stakeholders to see all the changes in code, design and/or process in realtime as it happens rather than more traditional approach where system code changes are not deployed to production right away, but instead they sit in a different branch until they are ready. While this reduces the technical risk, it increases the business risk, because the stakeholders are not aware of what is happening to the system. • Continue researching and eventually implementing fitting Blockchain solution. • Map new system as close as possible to the existing one to minimize system disruption and ease of adoptation.
| Hummingbird | R1. Although at first glance drones look like the biggest challenge, it's the image processing and resources needed to accommodate such a system which will pose the greatest risk. R2. Transport Canada's UAV regulations. | I1. Using drones in indoor setting has come up as a potential issue. | • Access feasibility of virtual inspection by discussing with related domain experts. • Explore areas of opportunity through focus groups and engagement sessions with Cannabis domain experts • Establish a task team to define use cases. • Submit Solutions fund, Stream I proposal by October 19th, 2018. • Key Business Requirements and Features for MVP was completed January 25, 2019. • Develop Feasibility Report. Target end of January, 2019. • Initiate Options Analysis. Target end of February.
| Cipher | R1. Data fitness not amenable for machine learning and AI in existing state R2. Insufficient data volume to train machine |  | • Access feasibility of machine learning and AI to improve risk analaysis of inspection observations • Explore areas of opportunity through focus groups and engagement sessions with inspection SMEs from HPCD • Establish a task team to define use cases. • Submit Solutions fund, Stream I proposal by October 19th, 2018. • Key Business Requirements and Features for MVP was completed in February, 2019. • Develop Feasibility Report. Target end of March, 2019. • Initiate Options Analysis. Target end of March
Instructions: Please list and describe your risks and issues. Use the legend below to assign an impact to each.
High
Medium
Low

## Progress Chart
Progress Chart
|  | Gate 1 |  |  |  | Gate 2 | [6 empty] | Gate 3 |  |  |  | Gate 4 |  |  | Gate 5
|  | Idea Generation |  |  |  | Project Initiation | [6 empty] | Project Planning |  |  |  | Project Execution |  |  | Project Close Out
IP# | Project | Proposal | Investment Proposal Form | Concept Case | Costing | Business Requirements | Project Charter | Business Case | Options Analysis | PCRA | Costing Model | Project Brief | PMP | Updated PCRA | Update Costing Model | Functional Requirements | Risk Register | Issues Log | Transition Plan | Project Closeout | Lessons Learned | Benefits Realization | Finalized Project Documentation
103 | Single Window Initiative
628 | Establishment Licensing and Inspections (BREAD lead)
435 | Drug Shortages
A01 | RORB Data Analytics & Business Analysis |  |  |  |  | N/A |  |  | N/A | N/A
A02 | RORB Electronic Licensing and Global Supply Chain Mapping
A03 | Enabling Compliance and Enforcement Program Delivery
A04 | RORB Aging IT (Stabilization/Modernization/Transformation)
A05 | Drug and Health Product Inspections Database
A06 | Modernizing the RORB Employee eToolkit
IP701 | Border IM/IT Modernization
IP704 | Quality Management System | [6 empty] | in progress | In progress |  | in progress
A07 | GCdocs
SF2018/19-007 | Project Cyclops
705 | DAS Modernization
| Gadget Phase I | [5 empty] | draft | draft
Hummingbird
| Cipher | [5 empty] | draft | draft
Legend
To do
In progress
Done
N/A

## Critical Dates
Critical Dates
IP# | Project | PM | Gate | Director Meeting | DG Steering Committee | BEC-FPR | Pre DG-IP | DG Forum | DG-IP | EC-FIPT | Comments
103 | Single Window Initiative | Mark Mackay | 5 |  |  |  | Early Jan |  | 2019-01-11 | 2019-03-28 | Project is now closed through DG-IP
628 | Establishment Licensing and Inspections | John Rezk / Mark Mackay | 2 | [7 empty] | Dates for the next Gate visit have not yet been established
435 | Drug Shortages | Amy McDonald | 4 | [7 empty] | Execution/Sustain Mode
A01 | RORB Data Analytics & Business Solutions | San Nguyen | 1 |  |  | Q4 FY 17/18 | N/A |  | N/A |  | Not an IP
A02 | Global Supply Chain Mapping + RORB Electronic Licensing | Mark Mackay | 0 | [7 empty] | Pausing until there is more clarity on the schedule and scope sequencing for IP628
A03 | Enabling Compliance and Enforcement Program Delivery | Eric Grandmaison | 1 |  |  | Q4 FY 17/18 | Q4 FY 17/18 | 2018-06-26 | Q1 FY 18/19
A04 | RORB Aging IT (Stabilization/Modernization/Transformation) | All | 0 |  |  | TBD | TBD |  | TBD
A05 | Drug and Health products inspections database. | Amy McDonald | 1 |  |  | Q4 FY 17/18 | Q4 FY 17/18 |  | Q1 FY 18/19 |  | U250K
A06 | Modernizing the RORB Employee eToolkit | Kenny McDowell | 0 |  |  |  | N/A |  | N/A |  | Not an IP
IP701 | Border Compliance IT Modernization | Irshad Mulla | 3 |  | Q4 FY 18/19 |  | Q4 FY 18/19 |  | Q4 FY 18/19 | Q4 FY 18/19 | Gate 3 expected in Mar 2019
IP704 | Quality Management System | Toufic Zayoun | 2 |  |  | Q4 FY 18/19 | Q4 FY 18/19 | Q4 FY 18/19 | Q4 FY 18/19 | Q4 FY 18/19 | OA Initiation on January 16 2019
N/A | RORB IM Strategic Plan | Alan Tam | N/A
A07 | GCdocs | Alan Tam | 4 |  | 2018-09-14 |  |  |  | 2018-09-17 |  | Endorsement rec'd at DG-IP. GCdocs implementation on Feb 5th.
705 | DAS Modernization | Mark Mackay | 2 | [5 empty] | 2019-05-21 | 2019-05-30 | Work is underway to prepare for Gate 2.
SF2018/19-007 | Project Cyclops | Irshad Mulla | N/A
A09 | Cost Recovery | San Nguyen | N/A | [7 empty] | All reports and datasets must be completed before implementation of new CR policy and fee structure on April 1st, 2019.
| Gadget Phase I | Peter Yoon (HC) Andriy Drozdyuk (NRC)
| Hummingbird | Peter Yoon
| Cipher | San Nguyen
Note: Not all committees are applicable for each project.